In accordance with Article 38(1) of the Law on the Planning System of the Republic of Serbia (*The Official Gazette of the Republic of Serbia*, No. 30/18) and Article 17(1) of the Law on Government (*The Official Gazette of the Republic of Serbia*, Nos. 55/05, 71/05 − correction, 101/07, 65/08, 16/11, 68/12 − CC, 72/12, 7/14 − CC, 44/14 and 30/18 − as amended),

The Government has adopted

ACTION PLAN   
FOR THE IMPLEMENTATION OF THE STRATEGY FOR CREATING AN ENABLING ENVIRONMENT FOR DEVELOPMENT OF CIVIL SOCIETY IN THE REPUBLIC OF SERBIA FOR THE PERIOD 2022-2030, FOR THE PERIOD 2022–2023

**1. INTRODUCTION**

The Action Plan for the implementation of the Strategy for Creating an EnablingEnvironment for Development of Civil Society in the Republic of Serbia for the period 2022–2030 for the period 2022-2023 (hereinafter: Action Plan) is a public policy document which is an integral part of the Strategy for Creating an Enabling Environment for Development of Civil Society in the Republic of Serbia 2022–2030 (*The Official Gazette of the Republic of Serbia*, No. 23/22) (hereinafter: Strategy), and was adopted at the Government session on 3 February 2022. The Action Plan contains an overview of overall and specific objectives and measures for exercising the defined objectives and measures, the authorities implementing the activities and their partners in implementing the activities, indicators, deadlines for the implementation of activities, sources of financing, and other methodological parameters.

The Action Plan contains the overall objective of the Strategy and four specific objectives.

**Overall objective**: Existing mechanisms for creating an enabling environment for the activities of civil society organizations strengthened and new mechanisms introduced

Specific objectives:

**Specific objective 1:** Ensure greater involvement of the civil sector in the decision-making process at all levels of government

**Specific objective 2**: Improved transparent financing and sustainability of the civil sector;

**Specific objective 3**: Ensure greater participation of CSO in the socio-economic development and acting in accordance with the principles of sustainable development;

**Specific objective 4:** Ensure greather participation of CSO in the European integration process.

**2. PROCESS OF DRAWING UP THE ACTION PLAN**

After adopting the Strategy, the Special Working Group for the -development of the Draft Action Plan for the implementation of the Strategy for an Enabling Environment for Development of Civil Society in the Republic of Serbia for period 2022–2030, for the period 2022-2023, consisting of representatives of state administration bodies, independent bodies and civil society organisations, as well as representatives of international organisations in the capacity of observers of the process of the development of the Action Plan, started to work on the development of the Draft Action Plan.

The process of development of the Draft Action Plan included a consultative process for representatives of associations and other civil society organisations, scientific research organisations, professional and other organisations, as well as representatives of state bodies and provincial bodies, local self-government bodies, representatives of economic operators and other stakeholders. A call for suggestions and comments during the consultations was published at the eConsultations portal, as well as on the website of the Ministry of Human and Minority Rights and Social Dialogue. Suggestions and comments relevant for drawing up the Action Plan could be submitted by any interested parties between 15 and 22 March 2022. The Report of the Consultation was uploaded on the website of the Ministry of Human and Minority Rights and Social Dialogue and the eConsultations portal.

The process of further development of the Draft Action Plan included a public debate. The Programme of Public Debate on the Draft Action Plan for the implementation of the Strategy for Creating an Enabling Environment for Development of Civil Society in the Republic of Serbia for period 2022–2030, for the period 2022-2023, with accompanying materials, was published at the eConsultations portal and the website of the Ministry of Human and Minority Rights and Social Dialogue, between 19 May and 8 June 2022. The Report on the Public Debate was uploaded on the website of the Ministry of Human and Minority Rights and Social Dialogue and the eConsultations portal.

The Strategy has one Overall objective and four specific objectives, which are achieved through 20 measures. The Action Plan entails the execution of 17 measures. Three measures are not included, because the period of realization of this Action Plan is shorter than two years, but their realization is to be included in one of the upcoming action plans.

Measures not included in this Action Plan are: One measure within specific objective 3: Measure 3.5 Improving citizens' awareness of the role of CSOs in socio-economic development, and two measures within specific objective 4: Measure 4.1 Continued and strengthening of active cooperation of public authorities participating in negotiations on European integrations and the National Convention and other CSO platforms, and Measure 4.7. Strengthening the transparency of CSO financing through the funds of local self-government units.

**3. FINANCIAL RESOURCES NECESSARY TO IMPLEMENT THE ACTION PLAN**

In 2022, financial resources were provided in the total amount of 529,250,000.00 RSD. In 2023, the amount of financial resources is to be 530,650,000.00 RSD, in accordance with the balance capacities of the budget of the Republic of Serbia. The total amount for the entire validity period of this Action Plan is 1,059,900,000.00 RSD.

All financial resources necessary for the realisation of the activities shown in the Draft Action Plan were provided in 2022 in accordance with the Law on Budget (*The Official Gazette of the Republic of Serbia*, No. 110/21). In 2023, financial resources will be planned in accordance with the limits defined the Ministry of Finance for all budget beneficiaries, within the cited budget sections and respective programmes which include the planning of financial resources for the realisation of activities indicated in this Action Plan. In that regard, this Action Plan does not require additional financial resources from the budget of the Republic of Serbia.

Certain activities are to be financed from donor funds. In this regard, in accordance with Article 58, paragraph 1, point 4), indent 3 of the Regulation on Methodology for public policy management, public policy and regulation impact analysis and content of individual public policy documents (*The Official Gazette of the Republic of Serbia*, No. 8/19), these measures shall be implemented conditionally, as they are financed from donor sources.

All the activities which are stated to be within the framework of the Programme which are realised with the financial resources provided in the budget entail regular activities by civil servants and state employees as prescribed for them, whether it is their participation in working groups or individual activity in monitoring the implementation of regulations or development of certain analyses, reports, data collection etc. and do no not require special budgeting.

The implementation of measures prescribed in this Action Plan will not affect international financial obligations of the country, since no borrowing has been planned. Allocated financial resources by measures are indicated in chapter 4. Action Plan.

**4. ACTION PLAN**

LIST OF ABBREVIATIONS

GS - General Secretariat of Government of the Republic of Serbia

MHMRSD - Ministry of Human and Minority Rights and Social Dialogue

MPALSG - Ministry for Public Administration and Local Self-Government

MCI - Ministry of Culture and Information

MoF – Ministry of Finance

MoLEVSA - Ministry of Labour, Employment, Veteran and Social Affairs

MYS - Ministry of Youth and Sport

MFA - Ministry of Foreign Affairs

MEP - Ministry of Environmental Protection

MESTD – Ministry of Education, Science and Technological Development

MEI - Ministry of European Integration

MJ - Ministry of Justice

MoI - Ministry of Interior

ME – Ministry of Economy

CIPE - Commissioner for Information of Public Importance

CPE - Commissioner for the Protection of Equality

PPS - Public Policy Secretariat

RLS - Republic Secretariat for Legislation

NAPA - National Academy for Public Administration

NES - National Employment Service

OITeG - Office for IT and E-Government

CSP - Centre for Social Protection

CCIS - Chamber of Commerce and Industry of Serbia

STGO - Standing Conference for Towns and Municipalities

NCEU - National Convention on the European Union

BOS – Belgrade Open School

NQF - National Qualification Framework

PROAEA - Centre for accreditation of publicly recognized organizers of adult education activities

CGC - Career guidance and counselling

IPA - Instrument for Pre-accession

|  |  |
| --- | --- |
| **PP document:** | **Strategy for Creating an Enabling Environment for the Development of Civil Society in the Republic of Serbia 2022–2030** |
| **Action Plan:** | **Action Plan for the implementation of the Strategy for Creating an Enabling Environment for the Development of Civil Society in the Republic of Serbia for period 2022–2030, for the period 2022-2023** |
| **Proposed by:** | **Ministry of Human and Minority Rights and Social Dialogue** |
| **Coordination and reporting by:** | **Ministry of Human and Minority Rights and Social Dialogue** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Overall objective:** Existing mechanisms for creating an enabling environment for the activities of civil society organizations strengthened and new mechanisms introduced | | | | | |
| Institution responsible for monitoring and control of realisation Ministry of Human and Minority Rights and Social Dialogue | | | | | |
| Indicator(s) at the level of an overall objective: | Unit of measurement | Source of verification: | Baseline value | Baseline year | Target value in the final year of the AP |
| - Compliance of the relevant regulatory framework with international standards  - Institutional framework of public administration bodies that enables an efficient cooperation with CSO  - Administrative practices aligned with the best comparative practices  - Overall social environment that is stimulating for the activity of CSO | YES/NO  YES/NO  YES/NO | Report on the implementation of the Action Plan for Chapter 23;  European Commission Progress Report on the Republic of Serbia in the EU Integration Process;  CSO reports;  Reports on the activities of the MHMRSD | NO | 2021 | YES |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Specific objective 1:** Ensure greater involvement of the civil sector in the decision-making process at all levels of government | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Human and Minority Rights and Social Dialogue; | | | | | | |
| Indicator(s) at the level of a specific objective (outcome indicator): | Unit of measurement | Source of verification | Baseline value | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| The participation of the civil sector in the decision-making process in the early phases has been increased on all levels | 0 – no impact  1 – low impact  2 – strong impact | Report on the implementation of the Regulatory Reform Programme | 0 | 2021 | 1 | 2 |

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 1.1 Improvement of the legal and institutional framework for further development of CSO in the decision-making process** | | | | | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Human and Minority Rights and Social Dialogue | | | | | | | | | | |
| Period of implementation 2022-2023 | | | | | Type of measure: Institutional-managerial-organisational | | | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | | Source of verification | Baseline value | | Baseline year | | Target value in 2022 | | Target value in the final year of the AP (2023) |
| Share of draft laws for which the public debate has been implemented in the total annual number of proposals of laws defined by the Government of Republic of Serbia | Percentage | | Reports of the General Secretariat of the Government of the Republic of Serbia | 35.7 | | 2020 | | 45 | | 55 |
| Percentage of public policy documents for which the public debate has been implemented in the total annual number of PPD defined by the Government of Republic of Serbia | Percentage | | Reports of the General Secretariat of the Government of the Republic of Serbia  Reports on the activities of the PPS | 83.3 | | 2021 | | 100 | | 100 |
| Number of sessions held by the Council for Cooperation and Development of the Civil Society | Number | | Minutes from the sessions  Reports on the activities of the Council | 0 | | 2021 | | 1 | | 4 |
| Source of funding of the measure | | Link to the programme budget | | | | | Total estimated financial resources in 000 RSD | | | |
| In 2022 | | In 2023 | |
| Budget of Serbia | | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001 | | | | |  | |  | |
| Donor funds | |  | | | | |  | |  | |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 1.1.1. Establishment of the Council for Cooperation and Development of the Civil Society and holding its regular sessions | MHMRSD | CSO | Q4 of 2022 | Budget of Serbia - general budget revenues and allowances  current employee expenses | 33-1002-110-0001 |  |  |
| 1.1.2. Annually update the data base of contact points for cooperation with CSO in all public administration bodies and make it publicly available | MHMRSD |  | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances  current employee expenses | 33-1002-110-0001 |  |  |
| 1.1.3. Develop the methodology and conduct a comprehensive research on the status of CSO in the Republic of Serbia and draw up report. | MHMRSD | Council for Cooperation and Development of the Civil Society | Q4 of 2023 | Donor funds |  |  |  |
| 1.1.4. Conduct an analysis of the implementation of the consultation process and the public debate for the purpose of possibly connecting them and thus improving both processes | MHMRSD | MPALSG  RLS  GS  PPS | Q4 of 2023 | Donor funds |  |  |  |
| 1.1.5. Developing a proposal for an improvement of the eConsultations portal in order for it to include an additional feature for the entry of data on the participation of CSO in Working Groups for drafting public policy documents and regulation proposals | MHMRSD | PPS | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances  current employee expenses | 33-1002-110-0001 |  |  |
| 1.1.6. Draw up and publish an annual report on the monitoring of the implementation of the Guidelines for the inclusion of civil society organisations in the working groups for drafting public policy documents and regulation proposals | MHMRSD |  | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances  current employee expenses | 33-1002-110-0001 |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 1.2:** **Impruving the capacities of public administration bodies for inclusion of CSO in the process of the development, application, monitoring of the application and evaluation of the effects of public policies and regulations** **Improving the capacity of public administration bodies to involve CSOs in the process of drafting, implementing, monitoring the implementation and evaluating the effects of public policies and regulations** | | | | | | | |
| Authority in charge of the implementation (coordination of the implementation) of the measure: Ministry of Human and Minority Rights and Social Dialogue | | | | | | | |
| Period of implementation 2022-2023 | | | | Type of measure: Informative-educational | | | |
| Indicator(s) at the level of a measure (result indicator): | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of implemented trainings for employees in the public administration bodies on the inclusion of CSO in the process of the development, implementation, monitoring of the implementation and evaluation of the effects of public policies and regulations | Number | Reports on the activities of the MHMRSD  NAPA reports | 5 | | 2021 | 6 | 8 |
| Number of employees in public administration bodies who are trained for inclusion of CSO in the process of the development, impelementation , monitoring of the implementation and evaluation of the effects of public policies and regulations | Number | Reports on the activities of the MHMRSD | 50 | | 2021 | 60 | 70 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of funding of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 59-0615-110-0001 |  |  |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 1.2.1. Implement trainings for contact points for cooperation with CSO on the national and local level on the inclusion of CSO in the process of drafting, implementation, monitoring of the implementation and evaluation of the effects of public policies and regulations | MHMRSD | CSO    BOS | Q4 of 2023 | Donor funds |  |  |  |
| 1.2.2. Number of implemented trainings for employees in the local self-government bodies on the inclusion of CSO in the process of the development, implementation, monitoring of the implementation and evaluation of the effects of public policies and regulations | MHMRSD | SCTM  LSGU | Q4 of 2023 | Donor funds |  |  |  |
| 1.2.3. Implement trainings for employees in the public administration bodies on the public participation in the process of drafting public policy documents and regulation proposals which entails the inclusion of  CSO in the process of the development, implementation , monitoring of the implementation and evaluation of the effects of public policies and regulations | NAPA | MHMRSD | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current expenses | 59-0615-110-0001 |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 1.3:** **Improving the capacity of CSOs to understand the role, competencies and functions of public administration and participation in the process of drafting, implementing, monitoring the implementation and evaluation of public policy documents and regulations** | | | | | | | |
| Authority in charge of the implementation (coordination of the implementation) of the measure: Ministry of Human and Minority Rights and Social Dialogue | | | | | | | |
| Period of implementation 2022-2023 | | | | Type of measure: Informative-educational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of representatives of CSO annually trained for the inclusion of CSO in the process of the development, implementation , monitoring of the implementation and evaluation of the effects of public policies and regulations | Number | Reports on the activities of the Ministry of Human and Minority Rights and Social Dialogue | 0 | | 2021 | 40 | 50 |
| Number of trainings implemented for CSO for understanding the role, competences and functions of the public administration and participation in the process of the development, implementation , monitoring of the implementation and evaluation of the effects of public policies and regulations | Number | Reports on the activities of the Ministry of Human and Minority Rights and Social Dialogue | 0 | | 2021 | 3 | 4 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of funding of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001 |  |  |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 1.3.1. Develop a plan and programmes of trainings for CSO for understanding the role, competences and functions of the public administration and participation in the process of the development, implementation , monitoring of the implementation and evaluation of the effects of public policies and regulations | MHMRSD | CSO | Q1 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 1.3.2. Regularly implement trainings for CSO for understanding the role, competences and functions of the public administration and participation in the process of the development, implementation , monitoring of the implementation and evaluation of the effects of public policies and regulations | MHMRSD | CSO  BOS | Q4 of 2023 | Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 1.4:** **Improving the image of the civil sector in the media and the public** | | | | | | | |
| Authority in charge of the implementation (coordination of the implementation) of the measure: Ministry of Culture and Information | | | | | | | |
| Period of implementation 2022-2023 | | | | Type of measure: Informative-educational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of supported projects for production of media content in open competitions in the field of public information | Number | Decisions of the Ministry of Culture and Information on the allocation of financial resources in open competitions in the field of public information | 0 | | 2021 | 5 | 7 |
| Number of produced media contents on CSO activities in the media | Number | Report of the Ministry of Culture and Information on a realised open competition in the field of public information | 0 | | 2021 | 10 | 20 |
| Number of institutions, CSO and media included in social dialogue on the topic of improving the public image of CSO | Number | Reports on the activities of the Ministry of Human and Minority Rights and Social Dialogue | 0 | | 2021 | 30 | 35 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 29-1204-820-0001  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001 | 2500 | 3500 |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 1.4.1. In open competitions of the MCI for production of media contents, define the role and importance of civil society organisations as the priority topic | MCI | CSO  MHMRSD | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances | 29-1204-820-0001 | 2500 | 3500 |
| 1.4.2. Organise social dialogue on the topic of the improvement of the image of the civil sector in the media for the purpose of an improved media reporting on and public understanding of the role of CSO | MHMRSD | CSO  MCI | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current expenses | 33-1002-110-0001 |  |  |
| 1.4.3. Conduct activities according to the binding recommendations from the social dialogue | MHMRSD | CSO  MCI | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current expenses | 33-1002-110-0001 |  |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Specific objective 2:** **Improved transparent financing and sustainability of the civil sector** | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Human and Minority Rights and Social Dialogue | | | | | | |
| Indicator(s) at the level of a specific objective (outcome indicator) | Unit of measurement | Source of verification | Baseline value | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Improved transparency of the financing of programmes and projects of CSO from budgetary resources and monitoring of the implementation and evaluation of projects | YES/NO | Reports on the activities of the MHMRSD  Reports on the implementation of the Action Plan for Chapter 23  Data from the Annual Summary Report on Budget Expenditures Provided as Support to the Programme and Project Activities of the Associations and Other Civil Society Organisations from the Budget of the Republic of | NO | 2021 | NO | YES |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 2.1 Improvement of the stimulating regulatory framework and administrative practices for the transparency of financing and financial sustainability of the civil sector** | | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Human and Minority Rights and Social Dialogue | | | | | | | |
| Period of implementation 2022-2023 years | | | | Type of measure: Regulatory | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Amendments to regulations have been adopted to ensure the reclassification of the budgetary line 491, in order to clearly separate the dotations to associations, endowments and foundations from dotations to political parties, religious communities, ethnic communities and every other entity whose financing is regulated by special regulations | Yes/No  No/Yes | Reports on the activities of the MoF  Official Gazette of the Republic of Serbia | No | | 2021 | Yes | Yes |
| Number of rejected appeals of CSO to the results of open competitions compared to the total number of appeals | Number | Report of the MHMRSD on the number of rejected appeals at the central government level | The baseline value is in the process of being defined and will be defined after the process of data collection, by the end of 2022. | | 2021 |  |  |
| The percentage of allocated financial resources through an open competition compared to other procedures of allocation. | Percentage | Annual Summary Report on Budget Expenditures Provided as Support to the Programme and Project Activities of the Associations and Other Civil Society Organisations from the Budget of the Republic of | 0 | | 2020 | 70% | 80% |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 3-0614-140-0001  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 0404-560-0004-41  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001 | 600  400 | 200 |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 2.1.1. Reclassification of the budgetary line 481 on the sixth level of budgetary classification, in order to clearly separate the dotations to associations, endowments and foundations from dotations to political parties, religious communities, ethnic communities and every other entity whose financing is regulated by special regulations | MoF | MHMRSD | Q4 of 2022 | Budget of Serbia – current expenses |  |  |  |
| 2.1.2. Conduct an analysis of the application of the Law on Games of Chance, including the possibility of changing the law in such a manner that a certain portion of financial resources is also used for financing other programmes of public interest implemented by the CSO, with no harmful consequences on the organisations of persons with disabilities and other associations aimed at improving the socio-economic and social status of persons with disabilities and other persons in social need. | MoF | MHMRSD | Q3 of 2023 | Donor funds |  |  |  |
| 2.1.3. Collect data on the public financing of CSO and ensure a quality compilation and regular publication of Annual Summary Report on Budget Expenditures Provided as Support to the Programme and Project Activities of the Associations and Other Civil Society Organisations from the Budget of the Republic of, with recommendations | MHMRSD | All public authorities which finance CSO from budgetary resources | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances –  current employee expenses | 33-1002-110-0001 |  |  |
| 2.1.4. Conduct an analysis of the alignment of the acts of national authorities on financing associations and other CSO on the basis of sectoral regulations or laws, taking decisions from the Regulation as an example of good practice in accordance with the Conclusion on the need to align the regulations of the Government and public administration bodies which govern the financing of programmes/projects in certain fields with the Regulation on the funds for promoting the programme or the missing portion of the funds for financing a programme of public interest executed by the associations (Conclusion No. 05 Number 401-8330/2018-1). | MHMRSD | Authorities which finance CSO on the basis of sectoral regulations | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances | 33-1002-110-0001 |  | 200 |
| 2.1.5. Improved application of the Public call Calendar in such a manner that ensures a review of the planned and approved support to CSO from budgetary resources on the annual level | MHMRSD | OITeG | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances | 3-0614-140-0001 | 600 |  |
| 2.1.6. Develop criteria and guidelines for providing non-financial support to civil society organisations | MHMRSD | MoF | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances | 33-1002-110-0001 | 400 |  |
| 2.1.7. Promote and monitor the application of guidelines for providing non-financial support to civil society organisations and provide support to authorities for their implementation | MHMRSD |  | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances –  current employee expenses | 33-1002-110-0001 |  |  |
| 2.1.8. Organise social dialogue on the topic of transparent financing of civil society organisations from the budget of the Republic of Serbia | MHMRSD | MoF  SCTM  CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances | 33-1002-110-0001 |  |  |
| 2.1.9. Amend the by-law which defines the criteria for the determination of activities which affect the environment according to the level of negative environmental impact arising from the performance of the activities, and the amounts of fees | MEP | CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 25-0404-560-0004 |  |  |
| 2.1.10. Organise social dialogue on the topic of improving the sustainability of CSO through the development of cooperation with LSGU and use of the available funds of LSGU and international donors | MHMRSD | MEI  LSGU    SCTM  CSO | Q4 of 2023 | Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 2.2:** **Improvement of personnel and expert capacities of the public administration for planned and transparent allocation, monitoring and evaluation of the allocation of budgetary resources intended for programmes and projects of CSO and the level of achievement of the set objectives** | | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Human and Minority Rights and Social Dialogue | | | | | | | |
| Period of implementation 2022 - 2023 | | | | Type of measure: Institutional-managerial-organisational and Informative-educational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of implemented trainings for employees of public administration bodies for planned and transparent allocation, monitoring and evaluation of the allocation of budgetary resources intended for projects of CSO | (Annual) number | NAPA reports  LSGU reports | 4 | | 2021 | 50 | 70 |
| Number of employees of public administration bodies who are trained for planned and transparent allocation, monitoring and evaluation of the allocation of budgetary resources intended for programmes and projects of CSO | (Annual) number | NAPA reports  Reports on the activities of the MHMRSD  Reports on the activities of STGO | 98 | | 2021 | 98 | 120 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 59-0615-110-0001  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001 |  |  |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 2.2.1. Implement trainings for planning and transparent allocation, monitoring and evaluation of the allocation of budgetary resources and the level of achievement of set objectives for employees in the public administration | NAPA | MHMRSD | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current expenses | 59-0615-110-0001 |  |  |
| 2.2.2. Implement trainings for employees in the public administration on the topic of drawing up annual reports in accordance with the Law on Free Access to Information of Public Importance | MHMRSD | CIPE  NAPA | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 2.2.3. Implement trainings for planned and transparent allocation, monitoring and evaluation of the allocation of budgetary resources and the level of achievement of set objectives for employees in LSGU | MHMRSD | NAPA  LSGU  SCTM | Q4 of 2023 | Donor funds |  |  |  |
| 2.2.4. Implement trainings for employees in LSGU on the topic of drawing up annual reports in accordance with the Law on Free Access to Information of Public Importance | MHMRSD | CIPE  NAPA  LSGU  SCTM | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 2.3:** **Improving the professional capacity of CSOs for transparent management of allocated budget funds Enhancement of expert capacities of CSO for transparent management of allocated budgetary means** | | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Human and Minority Rights and Social Dialogue | | | | | | | |
| Period of implementation 2022 - 2023 | | | | Type of measure: Informative-educational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of implemented trainings on the topic of transparent management of allocated budgetary means on the annual level | Number | Reports on the activities of the MHMRSD | 0 | | 2021 | 2 | 4 |
| Number of trained CSO representatives on the topic of transparent management of allocated budgetary means on the annual level | Number | Reports on the activities of the MHMRSD | 0 | | 2021 | 40 | 45 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001 |  | 150 |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 2.3.1. Develop a training programme for CSO for transparent management of allocated budgetary means | MHMRSD | CSO | Q4 of 2022 | Budget of Serbia - general budget revenues and allowances | 33-1002-110-0001 |  | 150 |
| 2.3.2. Implement trainings for CSO for transparent management of allocated budgetary means | MHMRSD | CSO | Q4 of 2023 | Donor funds |  |  |  |
| 2.3.3. Implement trainings for CSO on the topic of drawing up annual reports in accordance with the Law on Free Access to Information of Public Importance | MHMRSD | CIPE  CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Specific objective 3:** **Ensured greather participation of CSO in the socio-economic development and acting in accordance with the principles of sustainable development** | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Human and Minority Rights and Social Dialogue | | | | | | |
| Indicator(s) at the level of a specific objective (outcome indicator) | Unit of measurement | Source of verification | Baseline value | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Improved strategic and regulatory framework which reinforces the role of CSO in fields of importance for the socio-economic development | YES/NO | Research on the status of CSO in the Republic of Serbia  *Official Gazette of the Republic of Serbia* | NO | 2021 | YES | YES |
| Defining public policies which are relying on the cooperation with CSO in accordance with the principles of sustainable development | YES/NO | *Official Gazette of the Republic of Serbia*  Research on the status of CSO in the Republic of Serbia | NO | 2021 | YES | YES |
| Improved awareness of citizens, in particular young people, on the social significance and effects of volunteering and philanthropic activities | YES/NO | Research on the status and needs of young people in the Republic of Serbia | NO | 2021 | YES | YES |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 3.1 Improvement the normative framework in the field of social protection, which is harmonized with the international standards and ensures the sustainability of services provided by CSO** | | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Labour, Employment, Veteran and Social Affairs | | | | | | | |
| Period of implementation 2022-2023 | | | | Type of measure: Institutional-managerial-organisational and regulatory | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Proposal of strategic framework in the field of social protection, harmonized with international standards and taking into account the experiences of CSO so far as providers of services, has been drawn up | YES/NO | Report of the Ministry of Labour, Employment, Veteran and Social Affairs  *Official Gazette of the Republic of Serbia* | NO | | 2021 | YES | YES |
| Draft Law amending and supplementing the Law on Social Protection in accordance with a new strategic document, including accompanying by-laws | YES/NO | Report of the Ministry of Labour, Employment, Veteran and Social Affairs  *Official Gazette of the Republic of Serbia* | NO | | 2021 | YES | YES |
| Increased number of licensed CSO as providers of social protection services | Percentage | Report of the Ministry of Labour, Employment, Veteran and Social Affairs  Report of the Republic Institute for Social Protection and the Provincial Institute for Social Protection | 198 | | 2021 | 10 | 10 |
| Increased number of beneficiaries of services in the community which allow beneficiaries of the social protection system who need a more intense support to satisfy most of their needs in a natural environment | Number | Annual report on the activities of Social welfare centres  Annual report on the activities of providers of social protection services of the Republic Institute for Social Protection  Annual report on the activities of providers of social protection services of the Provincial Institute for Social Protection | 24,782 | | 2021 | 25,402 | 26,022 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 30-0902-070-0004  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 30-0902-070-0005  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001 | 500,000 | 500,000 |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 3.1.1. Draw up a proposal of a new strategic framework in the field of social protection which ensures the pluralism of providers of services | MoLEVSA | CSO | Q4 of 2023 | Donor funds |  |  |  |
| 3.1.2. Draw up the Draft Law amending and supplementing the Law Social Protection in accordance with a new strategic document, which:  - separates the role of the procurer of services from the role of the provider of services for the purpose of including CSO in the evaluation of services which are provided at the local level;  - improves the rules for licensing the provider of services;  - defines clear procedures for quality control of the social protection services of all providers | MoLEVSA |  | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 30-0902-070-0005 |  |  |
| 3.1.3. Adopt by-laws whose adoption is prescribed in the new Law amending and supplementing the Law on Social Protection | MoLEVSA |  | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 30-0902-070-0005 |  |  |
| 3.1.4. Align the relevant laws governing social protection with a new strategic framework in the field of de-institutionalisation | MoLEVSA |  | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 30-0902-070-0005 |  |  |
| 3.1.5. Implementation of the legal obligation of planning professional development and ensuring financial resources for the realisation of trainings in the annual professional development plan | MoLEVSA | Institute for Social Protection  Serbian Social Protection Chamber  CSP | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 30-0902-070-0005 |  |  |
| 3.1.6. Ensure financial resources of LSGU through target transfers for the development of support services, in particular services of personal assistants in local communities, housing services with support for persons who are leaving social protection institutions | MoLEVSA | LSGU | Q1 of 2023 | Budget of Serbia - general budget revenues and allowances | 30-0902-070-0004 | 500,000 | 500,000 |
| 3.1.7. Establishment of mechanisms for the consultative process for CSO for drawing up PPD on sustainable development of the Republic of Serbia | MHMRSD | CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 3.1.8. Conduct social dialogue on sustainable development of the Republic of Serbia with representatives of CSO | MHMRSD | CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 3.1.9. With CSO, review the analytical bases for drawing up PPD on the sustainable development of the Republic of Serbia | MHMRSD | SCTM  LSGU | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 3.1.10. Raising awareness on the level of local self-governments and CSO on sustainable development objectives - Agenda 2030 | MHMRSD | SCTM  LSGU | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 3.1.11.Develop the institutional space and platform for civil society for the purpose of joint adoption of decisions on the elimination of the consequences of the COVID-19 pandemic on human and labour rights, human life and health, mental state of the population and other challenges which may cause inequality, poverty and unemployment | MHMRSD | CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 3.1.12. Implement trainings of employees in social protection institutions using the CSO expertise in working with vulnerable and multiply marginalised groups for the purpose of improving the application of international standards in practice. | MoLEVSA | Social protection institutions Institute for Social Protection  LSGU | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 30-0902-070-0005 |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 3.2 Improvement of the overall regulatory framework of importance for philanthropy, including tax regulations, transparency and visibility of philanthropic activities** | | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Human and Minority Rights and Social Dialogue | | | | | | | |
| Period of implementation 2022 - 2023 | | | | Type of measure: Regulatory and informative-educational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 (t+1) | Target value in the final year of the AP (2023) |
| Publicly available systematic data on the effects of philanthropic activities | Serbia’s ranking (on a scale from 0 to 140) | World Giving Index; | 48 | | 2021 | 47 | 46 |
| Philanthropic activities by various groups of donors | Number | Reports  Catalyst Balkans - Annual Report on the status of charity | 4055 | | 2021 | 4100 | 4200 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001 |  |  |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 3.2.1. Collection of data for the purposes of initiating the improvement of the legal framework for group financing on the basis of donations (Crowdfunding) | MHMRSD | MoF | Q4 of 2023 | Budget of Serbia |  |  |  |
| 3.2.2. Organise social dialogue in the field of philanthropy as benefits for the common good | MHMRSD | CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 3.2.3. Compile a specific and special form for reporting of legal persons to the Tax Administration on the allowances for the common good which would enable accurate reporting by legal persons and provide a better basis for controlling those kinds of allowances | MoF | CSO | Q4 of 2023 | Budget of Serbia – current expenses |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 3.3 Defining a comprehensive regulatory framework which governs the social (solidarity) entrepreneurship, which ensures the diversity of financing CSO and the use of the the potential of socially responsible business activity** | | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Labour, Employment, Veteran and Social Affairs | | | | | | | |
| Period of implementation 2022 - 2023 | | | | Type of measure: Regulatory | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Acts governing social entrepreneurship and taking into account the subjects of social entrepreneurship have been adopted | YES/NO | *Official Gazette of the Republic of Serbia*  Report of the Council for Social Entrepreneurship | NO | | 2021 | YES | YES |
| Number of the sessions held by the Council for Social Entrepreneurship | Number | Minutes from the sessions  Reports on the activities of the Council | 0 | | 2021 | 2 | 4 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia |  |  |  |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 3.3.1. Hold regular meetings of the Council for Social Entrepreneurship | MoLEVSA | Subject of social entrepreneurship  CSO | Q4 of 2023 | Donor funds |  |  |  |
| 3.3.2. The social entrepreneurship development programme has been adopted | MoLEVSA | Council for Social Entrepreneurship | IV quarter of 2022. | Donor funds |  |  |  |
| 3.3.3. Organising round tables on public policies in the field of social entrepreneurship | MoLEVSA | CSO  ME  Council for Social Entrepreneurship  SCTM | Q4 of 2023 | Donor funds |  |  |  |
| 3.3.4. Promote social entrepreneurship and good practices in this field | MoLEVSA | CSO  MHMRSD  ME  Council for Social Entrepreneurship  SCTM | Q4 of 2023 | Donor funds |  |  |  |
| 3.3.5. Social Entrepreneurship Info-day | CCIS | CSO  MoLEVSA  MHMRSD | Q4 of 2022 | Budget of CCIS[[1]](#footnote-1) current expenses |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 3.4 Improvement of the normative framework governing volunteering in accordance with international standards, including sectoral regulations** | | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Labour, Employment, Veteran and Social Affairs | | | | | | | |
| Period of implementation 2022 - 2023 | | | | Type of measure: Regulatory and informative-educational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Improved regulatory framework governing volunteering | NO/YES | Report on the activities of the Ministry of Labour, Employment, Veteran and Social Affairs  *The Official Gazette of the Republic of Serbia* | NO | | 2021 | YES | YES |
| Increased number of volunteers belonging to the young population in the Republic of Serbia | Percentage | Report of the Statistical Office of the Republic of Serbia  Research on the status and needs of young people by the MYS | 27 young people volunteered | | 2021 | 28 | 29 |
| Amount of stimulating measures and programmes promoting/supporting volunteering among the young population | amount | Report of the Ministry of Youth and Sport | 22 million RSD | | 2021 | 22 million RSD | 23 million RSD |
| Increased percentage of young people with an awareness on the importance and effects of volunteering and philanthropic activities | Percentage | Research on the status and needs of young people in the Republic of Serbia | 58 | | 2021 | 62 | 67 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 30-0802-410-0002  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 31-1302-810-0005 | 22,000 | 23,000 |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 3.4.1. Adopt the Law on Volunteering aligned with the international standards | MoLEVSA |  | Q1 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 30-0802-410-0002 |  |  |
| 3.4.2. Implementation of stimulating measures and programmes supporting volunteering | MYS | Competent ministries  MoLEVSA  National body for the development of volunteering  CSO | Q4  2023 | Budget of Serbia - general budget revenues and allowances | 31-1302-810-0005 | 22,000[[2]](#footnote-2) | 23,000[[3]](#footnote-3) |
| 3.4.3. Improved environment which supports and promotes volunteering | MoLESVA | CSO  MYS  National body for the development of volunteering | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 30-0802-410-0002 |  |  |
| 3.4.4. Implement trainings for organisers of volunteering | MYS |  | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - expenses are shown under activity 3.4.2 | 31-1302-810-0005 |  |  |
| 3.4.5. Organise promotional activities (e.g., conferences, public campaigns, round tables, dialogue...) | MYS | MoLESVA  CCIS  National body for the development of volunteering  CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - expenses are shown under activity 3.4.2 | 31-1302-810-0005 |  |  |
| 3.4.6. Improved availability of information on the results of volunteering activities through social networks | MYS | MoLESVA  CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - expenses are shown under activity 3.4.2 | 31-1302-810-0005 |  |  |
| 3.4.7. Implement a campaign on the importance and effects of volunteering targeting young people | MYS | MoESTD  MoLESVA  CSO | Q4 of 2022 | Budget of Serbia - general budget revenues and allowances - expenses are shown under activity 3.4.2 | 31-1302-810-0005 |  |  |
| 3.4.8. Conduct social dialogue on the role of CSO in the socio-economic development | MHMRSD | MoLEVSA  MYS  CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 3.6 Improving the role of CSO in the informal education in accordance with strategic documents and with the range of education on human rights** | | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry of Education, Science and Technological Development | | | | | | | |
| Period of implementation 2022 - 2023 | | | | Type of measure: Regulatory and informative-educational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Improved conditions for informal education in accordance with the strategic framework in the field of education | YES/NO | Reports of the Ministry of Education  Report on the implementation of the Education Development Strategy    CSO reports | NO | | 2021 | NO | YES |
| Improved number of accredited programmes of informal education implemented by CSO entered into the NQF register – PROAEA sub-register | Number | NQF register – PROAEA sub-register  CSO reports; | 0 | | 2021 | 3 | 5 |
| Increased number of CSO with accredited programmes implementing trainings with employers included in dual education | Number | Reports on the implementation of the Education Development Strategy;  CSO reports | 0 | | 2021 | 3 | 5 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 26-2001-980-0001  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 26-2001-980-0016  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 26-2001-980-0012 | 950 | 1,000 |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 3.6.1. Increased number of CSO which, through participation in open competitions of the MoESTD, contribute to the development and improvement of education | MoESTD | CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 26-2001-980-0001 |  |  |
| 3.6.2. Increased number of CSO participating in open competitions for accreditation of the programme of permanent professional development of teachers, pedagogues and expert associates for the purpose of enhancing the competences of the education employees for the promotion of democratic values with children, students and attendees | MoESTD |  | Q4 of 2022 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 26-2001-980-0001 |  |  |
| 3.6.3. Improvement of the diversity of accredited CGC programmes and services and their adjustment to the needs of certain target groups by CSO | MoESTD | CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 26-2001-980-0001 |  |  |
| 3.6.4. Improvement of the availability of education on human rights through a more active participation of CSO in open competition for the realisation of programmes of relevance for education | MoESTD | CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances | 26-2001-980-0012 | 950 | 1,000 |
| 3.6.5 Improved number of accredited programmes of informal education implemented by CSO entered into the NQF register – PROAEA sub-register | MoESTD | NQF Agency  NQF register –  PROAEA  sub-register | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances | 26-2001-980-0016 |  |  |
| 3.6.6. Continued and strengthened active cooperation between public authorities and CSO in the field of informal education | MoESTD | MHMRSD  CSO  MYS | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 26-2001-980-0001 |  |  |
| 3.6.7. Implementation of a campaign for the purpose of raising awareness on the importance of lifelong informal education and possibilities of this kind of education through the CSO programmes | MoESTD | MYS | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current expenses | 26-2001-980-0001 |  |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Specific objective 4:** **Ensure greater participation of CSOs in the European integration process** | | | | | | |
| Institution responsible for monitoring and control of realisation: Ministry for European Integration | | | | | | |
| Indicator(s) at the level of a specific objective (outcome indicator) | Unit of measurement | Source of verification | Baseline value | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of CSO involved in the monitoring of negotiation chapters | Number | Reports on the implementation of action plans for respective negotiation chapters;  Reports from meetings of competent institutions for monitoring negotiation chapters.  NCEU report. | 0 | 2021 | 10 | 15 |
| Number of consultations with CSO for the purpose of programming and monitoring of the implementation of the financial resources of EU | Number | Report of the MEI and the competent authorities - authorised proposers of projects for IPA financing | 0 | 2021 | 5 | 10 |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 4.2: Improvement of the cooperation of CSO with public authorities in fields of importance for European integration through regular consideration of of of CSO proposals in order to use the expertise of CSO and implementing permanent dialogue with CSO** | | | | | | | |
| Authority in charge of the implementation (coordination of the implementation) of the measure: Ministry of Human and Minority Rights and Social Dialogue | | | | | | | |
| Period of implementation | | | | Type of measure: | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of organised public debates/consultations on laws in fields of importance for European integration in which CSO have participated | Number | Reports of public authorities on the implemented consultations  Independent reports of domestic and international CSO. | 3 | | 2021 | 5 | 5 |
| Number of dialogues organized with CSO in fields of importance for European integration, particularly the rule of law, protection of fundamental rights, fight against corruption and organised crime | Number | Reports of public authorities on the implemented consultations  Independent reports of domestic and international CSO | 10 | | 2021 | 10 | 10 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001 |  |  |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 4.2.1. Organise consultations and review proposals of CSO on laws in fields of importance for European integration | MHMRSD | MEI  Negotiating groups in each negotiation cluster  CSO  NCEU | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 4.2.2. Organising special meetings with CSO relating to any disputed issues on laws of importance for European integration | MHMRSD | MEI  Negotiating groups in each negotiation cluster  CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 4.3 Improvement of the public discourse on the role of CSO in European integration** | | | | | | | |
| Authority in charge of the implementation (coordination of the implementation) of the measure: Ministry for European Integration | | | | | | | |
| Period of implementation 2022 - 2023 | | | | Type of measure: Regulatory and educational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of published information on websites of public authorities on the role of CSO in EU integrations in appropriate fields, in accordance with their competences | Number | Independent reports of domestic and international CSO | 0 | | 2021 | 5 | 20 |
| Percentage of citizens who are informed on the role of CSO in the field of EU integration | Percentage | Analysis of the public opinion by the Ministry of European Integration | 0 | | 2021 | 25 | 30 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 18-0601-110-0007  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 18-0601-110-0007 | 1,700 | 1,700 |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 4.3.1. Implement an analysis of the public opinion on the role of CSO in the field of EU integration, including recommendations for an improvement of the situation | MEI | CSO | Q3 of 2023 | Budget of Serbia - general budget revenues and allowances | 18-0601-110-0007 | 1,700 | 1,700 |
| 4.3.2. Create a unified record of contact points for the cooperation with CSO in authorities which participate in Negotiation Groups for the purpose of collection of data on the joint activities with CSO in the field of EU integrations | MEI | CSO | Q2 of 2022 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 18-0601-110-0007 |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 4.4 Improving the position of CSOs by providing effective legal protection for members of CSOs and human rights defenders** | | | | | | | |
| Authority in charge of the implementation (coordination of the implementation) of the measure: Ministry of Justice | | | | | | | |
| Period of implementation | | | | Type of measure: | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of threats/attacks on members of CSO and defenders of human rights | Number | Independent reports of domestic and international CSO  Annual report of the Protector of Citizens | 73 | | 2021 | 60 | 50 |
| Number of consultative meetings relating to the improvement of the efficiency of the legal protection for members of CSO and defenders of human rights | Number | CSO reports;  Reports of competent ministries | 0 | | 2021 | 2 | 4 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 12-1001-160-0012  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 33-1002-110-0001  BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 23-1602-360-0010 |  |  |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 4.4.1. Hold consultative meetings with representatives of CSO for the purpose of reviewing the situation relating to the threats/attacks on members of CSO who deal with human rights and the application of preventive measures | MHMRSD | MJ  MoI  Commissioner for the Protection of Equality  CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 33-1002-110-0001 |  |  |
| 4.4.2. Implement activities for the purpose of the enhancement of capacities of CSO for initiating proceedings for the protection of discrimination | CPE | MHMRSD  CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 12-1001-160-0012 |  |  |
| 4.4.3 Organise round tables with CSO, two times a year, on the implementation of activities from the sub-chapter Fundamental Rights from the revised Action Plan for Chapter 23 | MJ | MHMRSD  CSO | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances - current employee expenses | 23-1602-360-0010 |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 4.5 More intensive involvement of CSOs in the process of programming and preparation for the use of structural funds and other EU funds** | | | | | | | |
| Authority in charge of the implementation (coordination of the implementation) of the measure: Ministry for European Integration | | | | | | | |
| Period of implementation 2022 - 2023 | | | | Type of measure: Institutional-managerial-organisational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of CSO in the process of programming and preparation for using structural funds and other EU financial resources | Number | Reports of competent ministries  MEI report  Independent reports of domestic and international CSO | 0 | | 2021 | 10 | 15 |
| Number of trainings intended for CSO on programming and preparation for using structural funds and other EU financial resources, which also include cooperation with public authorities | Number | MEI report | 0 | | 2021 | 2 | 3 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia |  |  |  |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 4.5.1. Organise meetings of representatives of the MEI with representatives of CSO who deal with the subject in question, dedicated to programming and preparation for using structural funds and other EU financial resources | MEI | CSO | Q4 of 2023 | Donor funds |  |  |  |
| 4.5.2. Number of CSO in the process of programming and preparation for using structural funds and other EU financial resources | MEI | CSO  MHMRSD | Q4 of 2023 | Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure 4.6 Strengthening citizens' awareness of the EU integration process through cooperation with CSOs** | | | | | | | |
| Authority in charge of the implementation (coordination of the implementation) of the measure: Ministry for European Integration | | | | | | | |
| Period of implementation 2022 - 2023 | | | | Type of measure: Informative-educational | | | |
| Indicator(s) at the level of a measure (result indicator) | Unit of measurement | Source of verification | Baseline value | | Baseline year | Target value in 2022 | Target value in the final year of the AP (2023) |
| Number of joint activities of public authorities and CSO aimed at enhancing the awareness of citizens on the process of EU integration | Number | Report of the MEI and other competent authorities  Survey of the public opinion of the MEI | 0 | | 2021 | 5 | 10 |
| Percentage of public understanding of the benefits of EU accession in every day life | Percentage | Survey of the public opinion of the MEI | 0 | | 2021 | 25 | 30 |

|  |  |  |  |
| --- | --- | --- | --- |
| Source of financing of the measure | Link to the programme budget | Total estimated financial resources in 000 RSD | |
| In 2022 | In 2023 |
| Budget of Serbia | BUDGET OF SERBIA - GENERAL BUDGET REVENUES AND ALLOWANCES - 18-0601-110-0007-42 | 1,100 | 1,100 |
| Donor funds |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title of activity: | Authority implementing the activity | Partners in the implementation of the activity | Deadline for the completion of the activity | Source of finance | Link to the programme budget | Total estimated financial resources by sources in 000 RSD | |
| 2022 | 2023 |
| 4.6.1. Conduct a survey on the public understanding of the benefits of EU accession in every day life | MEI | CSO | Q3 of 2023 | Budget of Serbia - general budget revenues and allowances - expenses are shown under activity 4.3.1 | 18-0601-110-0007 |  |  |
| 4.6.2. Organise promotional activities relating to the current situation in the process of Serbia’s accession to the EU | MEI | CSO  NCEU | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances | 18-0601-110-0007 | 800 | 800 |
| 4.6.3. Organise info-days on IPA 3 and the Cross-Border Cooperation Programme for representatives of CSO | MEI | MoF | Q4 of 2023 | Budget of Serbia - general budget revenues and allowances | 18-0601-110-0007 | 300 | 300 |

**5 FINAL PART**

This Acton Plan shall be published on the website of the Government, the eGovernment portal, and the website of the Ministry of Human and Minority Rights and Social Dialogue, within seven working days from the date of adoption.

This Action Plan shall be published in *The Official Gazette of the Republic of Serbia*.

05 No. 90-7170/2022-1

In Belgrade, 16 September 2022

G O V E R N M E N T

|  |  |
| --- | --- |
|  | PRIME MINISTER  Ana Brnabić |

1. The Chamber of Commerce and Industry of Serbia has the status of a legal person in accordance with the Law on the Chambers of Commerce, *The Official Gazette of the Republic of Serbia*, No. 112/15. Financial resources for the realisation of this activity are defined in accordance with the Law on the Chambers of Commerce. Realisation of this activity does not require additional financial resources but will be realised with the regular budgetary allowances. [↑](#footnote-ref-1)
2. Financial resources planned within the framework of the programme “*Mladi su zakon*” [↑](#footnote-ref-2)
3. Financial resources planned within the framework of the programme “*Mladi su zakon*” [↑](#footnote-ref-3)